## Reference Info
ABCDS Checkpoint Evaluation (Full Review)
For the resource table, bias and mitigation template, and additional details about sensitive variables and subgroup analysis, see the main ABCDS Checkpoint Evaluation Guide available here.

## Gm Submission Checklist v1.1
Principle/Category | First Checkpoint | G0 | G1 | G2 | Gm | Evaluation Criteria | Recommended Submission Material (Predictive Models)
General/Summary | G0 | Yes | Yes | Yes | Yes | The project team is confident in the tool’s clinical value & safety, usability, fairness, and regulatory standing, and recommends continued development/deployment. | • Summary of conclusions regarding clinical value & safety, usability, fairness, and regulatory posture • Description of risks of false positive and false negative results within the workflow • Overall recommendation to proceed with development or deployment
Clinical Value & Safety | G0 | Yes | No | No | No | The ABCDS software, in comparison to current state, has potential to improve clinical outcomes and/or processes at Duke Health. | Results of a retrospective validation on Duke patient data, including: • Description of key metrics used to evaluate model performance (concordance index, calibration metrics, sensitivity, PPV, etc.) • Calibration of model performance across the full range of predictions (calibration curve) • Justification for clinical decision thresholds, if applicable • Description of key metrics used to evaluate impact on clinical outcomes and/or processes (net benefit) • Comparison to the existing solution or workflow the algorithm is intended to replace, if applicable
Clinical Value & Safety | G0 | Yes | No | No | No | Plans for Silent Evaluation will inform the decision to proceed with pilot implementation in clinic. | Plans for prospective Silent Evaluation, including: • Success criteria to proceed to clinical implementation • Study design, including in/exclusion criteria, timeframe and sample size considerations • Plan for data analysis and data quality assessment • Description of chosen evaluation metrics and shell tables • Description of how the algorithm will deal with missing data
Clinical Value & Safety | G1 | No | Yes | Yes | Yes | Clinical users have confidence in the tool’s safety and impact on process and/or outcomes. | • Summary of methods and findings from clinical validation of the tool on a small, representative cohort of patients (e.g. chart review)
Clinical Value & Safety | G1 | No | Yes | No | No | During Silent Evaluation, the tool performs according to expectations from development and/or prior validation on a different patient population. | Results of prospective Silent Evaluation, including: • Demonstration that success criteria described in the Silent Evaluation Plan are met • Description of key metrics used to evaluate model performance (concordance index, calibration metrics, sensitivity, PPV, etc.) • Calibration of model performance across the full range of predictions (calibration curve) • Description of key metrics used to evaluate impact on clinical outcomes and/or processes (net benefit) • Comparison to the existing solution or workflow the algorithm is intended to replace, if applicable
Clinical Value & Safety | G1 | No | Yes | No | No | Plans are in place for a small-scale clinical implementation (Effectiveness Evaluation) that will demonstrate real- world impact prior to General Deployment. | Plan for Effectiveness Evaluation, including: • Success criteria to proceed into General Deployment • Study design, including in/exclusion criteria, timeframe and sample size considerations • Plan for data analysis and data quality assessment • Description of chosen evaluation metrics and shell tables
Clinical Value & Safety | G2 | No | No | Yes | No | During Effectiveness Evaluation, the tool performs according to expectations from Silent Evaluation. | • Demonstration that success criteria described in the Effectiveness Evaluation Plan are met • Description of key metrics used to evaluate model performance (concordance index, calibration metrics, sensitivity, PPV, etc.) • Description of key metrics used to evaluate impact on clinical outcomes and/or processes (net benefit) • Calibration of model performance across the full range of predictions (calibration curve)
Clinical Value & Safety | G2 | No | No | Yes | + | Plans are in place for continuous monitoring of the tool. | Maintenance/Monitoring plan, including: • Definitions of chosen metrics for performance, stability, clinical impact, and fairness and equity • Adoption measures for each use case (may be qualitative) • Recommendation on monitoring frequency • Criteria for sunsetting or updating the tool
Clinical Value & Safety | Gm | No | No | No | Yes | The tool’s performance and adoption are stable and aligned with expectations for continued General Deployment | • Current monitoring report with a brief executive summary highlighting main findings on model performance, stability, clinical impact, and adoption • Updated monitoring plan (if needed)
Fairness & Equity | G0 | Yes | + | + | + | The project team has considered potential sources of bias and taken steps to prevent or mitigate associated harms. | • Completed or updated bias analysis with bias management strategies • Rationale for decisions regarding sensitive variables as inputs • Summary of any new considerations re: fairness and equity
Fairness & Equity | G0 | Yes | + | + | + | A strategy has been articulated for ongoing fairness & equity subgroup analysis. | • List of clinical impact and model performance metrics to examine across subgroups with rationale • List of stratification variables with rationale
Fairness & Equity | G0 | Yes | Yes | Yes | Yes | Performance of the algorithm is acceptable across subgroups. | • Results of fairness & equity subgroup analysis with interpretation of findings
Fairness & Equity | G2 | No | Yes | + | + | The principles of fairness and equity are reflected in plans for implementation in the clinical workflow. | Plan to assess the tool’s implementation and adoption from the standpoint of fairness and equity, for example: • How will the project team assess whether the tool is used consistently by its intended users? • How will the project team assess whether the decisions made on the basis of the tool’s output are similar across subgroups? • How will the project team gather feedback pertaining to fairness and bias?
Regulatory Compliance | G0 | Yes | + | + | + | The project team understands how design, implementation, and proposed use may influence the tool’s potential to be considered Software as a Medical Device (SaMD). | • Initial regulatory assessment re: SaMD with justification (may be provided within an updated registration form).
Regulatory Compliance | G0 | Yes | + | + | + | IRB application plans (if any) are articulated for development. | Brief comment and IRB submission reference number(s) for model development and/or implementation.
Regulatory Compliance | G0 | Yes | + | + | + | High-level plans are in place for commercialization (if applicable). | • Brief summary of commercialization plans and partners, including timing for integration of any external partners • Data sharing agreement(s)
Regulatory Compliance | G1 | No | Yes | + | + | The project team has prepared a regulatory assessment re: Software as a Medical Device (SaMD). | • Materials supporting regulatory assessment including direct input and/orcollaboration with the Duke Office of Regulatory Affairs and Quality (ORAQ)and/or FDA, where applicable • Documentation of any changes potentially affecting the regulatorypathway, e.g. user interface design
Regulatory Compliance | G1 | No | Yes | + | + | Commercialization plans have been finalized (if applicable). | • Finalized commercialization plans/agreements for external use of algorithms developed at Duke
Regulatory Compliance | G1 | No | Yes | + | + | Agreements are in place with external developers (if applicable). | • Contractual terms for use of externally-developed algorithms at DukeHealth
Regulatory Compliance | G2 | No | No | Yes | + | The project team has an approved IRB protocol or documented exemption for clinical implementation. | • IRB submission reference number
Transparency | G0 | Yes | + | + | + | ABCDS registration is complete and up- to-date. | • Completed or updated ABCDS registration form
Transparency | G0 | Yes | + | + | + | Plans are in place for ongoing clinical and operational support. | • Description of staff and financial resources needed to ensure the tool’ssustainability • Line of support by an individual with a budget
Transparency | G0 | Yes | + | + | + | Modeling methods, data inputs, and output(s) are clearly explained. | •Description of training dataset with an explanation of time period,inclusion/exclusion criteria •List of all data elements (predictors, outcomes, other) used to develop orevaluate the model •Comments on data quality and limitations •Description of modeling methods and variable importance
Transparency | G1 | No | Yes | Yes | Yes | Any changes to the model(s), use case, and/or operationalization of the tool are communicated in advance. | • Documentation of any changes to the model or recommended threshold(s), actions/decisions the tool is intended to support, etc.
Usability, Reliability, & Adoption | G0 | Yes | + | + | + | The proposed workflow links the tool’s output(s) to clear decisions/actions and reflects understanding of the current workflow. | • Workflow SWIM diagram describing how the new tool will change the current process or standard of care • List of actions clinicians may take based on the tool’s output • Mock-up of the user interface
Usability, Reliability, & Adoption | G0 | Yes | Yes | Yes | Yes | Operational and clinical resources are in place and timelines established to proceed to the next ABCDS Lifecycle Phase. | • Completed resource table for the upcoming ABCDS Lifecycle Phase
Usability, Reliability, & Adoption | G0 | Yes | No | No | No | The technical environment is ready for Silent Evaluation. | • Technical feasibility summary with estimated timeline • Name of DHTS contact and short description of build requirements (if applicable) • Plans for operational qualification/testing of tool • Data flow diagram
Usability, Reliability, & Adoption | G1 | No | Yes | Yes | No | The tool is successfully operationalized within the chosen deployment platform. | Results of data quality assessment and operational qualification/testing or DHTS RITM #
Usability, Reliability, & Adoption | G1 | No | Yes | + | + | Feedback mechanisms are established to evaluate end user acceptance of the tool within the proposed workflow. | • Plan to evaluate acceptance of the proposed workflow incorporating model predictions and recommended actions • List of proposed adoption measures (may be qualitative) for each use case
Usability, Reliability, & Adoption | G1 | No | Yes | + | + | A training plan is in place and materials are available to educate end users on appropriate use of the tool. | • Training plan and materials, including instructions for accessing the model fact sheet5 and other transparency information • Screenshots of the interface
Usability, Reliability, & Adoption | G2 | No | No | Yes | No | Small-scale clinical implementation (Effectiveness Evaluation) demonstrates potential for adoption by intended users. | • Summary of adoption measures and feedback received from end users during Effectiveness Evaluation (may be qualitative)

## Data Validation (hidden)
Fully
Partially
Not at all
Yes
No
+